## Open AIs
description/description | Actionee | action / action | due date / date butoir | Status | Comment
Review and update Risk Register | ALL | AI_01_04 | 2012-06-22 | ongoing
Review timetable (in Project Management Plan) and advise SatOC of any potential delays or conflicts | ALL | AI_01_05 | 2012-06-22 | ongoing | Inputs received from CLS
Review plans for WP4000, WP5000 and consider how to validate / assess performance of all key processing steps | NOC, CLS | AI_01_15 | 2012-08-31 | ongoing | Should be included in DVP contributions
WP1000 and WP2000 to review available ESA information on CryoSat processing / products and identify gaps. | Starlab, TU Delft | AI_01_16 | 2012-12-13 | Completed | Draft PAR and DVP produced
WP2000 analysis to include identification of corrections needed on ESA FBR data | TU Delft | AI_01_22 | 2013-02-01 | Completed | Draft PAR and DVP produced
Develop possible assessment approach using simulated products. | ALL | AI_01_24 | 2012-11-30 |  | Action ongoing : "the S3 SPS has been installed on the CNES Linux Cluster. We have generated one simulation lasting 90 seconds in SAR mode over ocean. It tooks about 125 CPU hours … We need to carefully validate this SPS installation and to contact Salvatore to define the simulation context."
Provide from RADs along track parameters needed for WTC computation and validation | TU Delft | AI_01_25 | Spring 2013 | Completed?
Send PF a short note about low volume (< 25%) of LRM data retrieved in area to N of Britain. | DTU Space | AI_01_30 | 2012-12-03 |  | PF confirmed would still like to receive
Include recommendations on metrics for impact assessment in outputs of WP2000 | TU Delft | AI_01_32 | 2013-02-01 | Not included? | MN to check -discuss in MTR agenda item 3
To coordinate plans for WP4000 and WP5000 | CLS (SL) and NOC (CG) | AI_01_36 | 2013-03-30 | ongoing | email discussions
Provide SatOC with list of Expert Group members | ESA (JB) | AI_01_37 | 2013-02-22 | completed | JB has invited experts to coordinated CP4O mid-term review / SAR Altimetry Workshop
Review the outline proposals for additional work in Technical Proposal and ask more detail for those of interest | ESA | AI_01_38 | May 2013? | ongoing | Maintain and update list as annex to Project Plan
Need to agree a statement from the whole CP4O team that can be relayed to the Cryosat Mission management regarding the quality of ESA Cryosat products and the consequent problems in using these products in the Cryosat Plus project. | TU Delft/ SatOC | A2_2 | 2012-12-07 | completed | DC has generated draft and SD, JB have updated. Sent to C2 mission manager on 30/01/2013
CLS to review effort needed to lead WP2200 and 2400 and decide if they can do this | CLS | A2_3 | 2012-12-07 | time expired | Draft PAR and DVP produced
Include comment on Sandwell retracker in WP2000 review | NOC | A2_4 | 2012-12-07 | completed | included in CP4O_WP2200_NOC_input.docx
To be confirmed: To provide algorithm on generation of sigma-0? | MF | A2_5 | 2012-12-07
Advise NOC/SatOC of relevant initiatives that should be included in WP2000 review (LRM and SAR data over coastal and open ocean) | All | A2_6 | 2012-12-07 | completed | Draft PAR and DVP produced
Review Crysoat-2 document list when provided by Starlab | ALL | A2_7 | TBD
Check if RDSAR needs modification to work on real C-2 data. | Starlab | A2_8 | 2012-12-07 | ongoing | Waiting for the AI_01_22 ( WP2000 analysis to include identification of corrections needed on ESA FBR data) to be completed and also waiting for the FBR to arrive. Due date to be revised
To provide an Executive Summary of WP2000, including key findings / conclusions, before Christmas | TU Delft | A2_9 | 2012-12-21 | time expired? | Draft of PAR in preparation, 7th May
Produce document on σ0 calculation implemented in RADS | RS | A2_12 | 2012-12-07 |  | A summary in the PAR and reference to a 2011 paper - is that the most recent reference?
Source documentation on σ0 calculation implemented in IPF | ESA (SD, MF)? | A2_13 | 2012-12-07 |  | Same as A2_5?
Provide details on the IPF evolutions - as this could impact the FBR and the CalVal analysis | SatOC?ESA | A2_14 | TBD - ongoing | completed? | available through link at https://earth.esa.int/web/guest/missions/cryosat/ipf-baseline
CNES to respond to requests to modify CPP product as described in 4.33 | CNES | A2_15 | TBD | completed?
To update data requirements spreadsheet | All | A2_17 | 2012-12-14 | ongoing
Advise isardSAT / CNES (cc SatOC) on requirements for CPP SAR data in WP4000. Specify location (polygon) and time period. | All | A2_18 | 2012-11-30 | completed? | NOC and Starlab have provided requirements
Advise when (and if!) requested CPP data for WP4000 can be made available | FB | A2_19 | 2012-12-14 | completed | CPP data produced and available. See FP email 4th April
Identify best approach to allow for mispointing in CPP products retrieved for WP4000 | FB, RS | A2_20 | TBD | ongoing?
Provide (historic) CS-2 orbit files with time, lat, long (and if possible surface type) | ESA (SD, MF) | A2_22 | TBD |  | underway
Discuss how output and analyses of outputs from SPS scenarios can be incorporated into WP4000 | CNES, ESA, SatOC, NOC | A2_23 | 2013-01-27
Request that information be provided on which star trackers is used be made available (important for SARIN applications) | ESA (SD?) | A2_24 | 2012-12-07 | completed | Information is included in matlab routines provided by SD
CNES to make mispointing file available to CP4O, and communicate the estimates values of new biases in Roll and Pitch. | CNES | A2_25 | 14/12/12? | completed? | See emails between RS and NP ending 01/03/13
CNES and NOOA to iterate mispointing analyses and report back to CP4O team on recommendations for processing / retracking. | CNES, RS | A2_26 | TBD
Provide specifications of test data set coverage and approaches for product processing and validation for RDSAR and SAR Open Ocean themes in WP4000 | Starlab, CLS | A2_27 | 2012-12-14 | Completed | Included in DVP
Clarify what SAR open ocean validation data set can be provided by STARLAB under WP4400 | Starlab | A2_28 | TBD (06/13?) |  | to be clarified
Provide feedback to CLS on proposed assessment metrics for WP5000 | All | A2_29 | 2012-12-14 | ongoing
Provide feedback to CLS on proposed approach to polar oceanography and sea floor altimetry in WP5000 | DTU | A2_30 | 2012-12-14 | ongoing
Liaise with CB to find information on internal path delay (for LRM and SAR) | SatOC | A2_31 | 2012-12-07 |  | Request sent to CB
Advise SatOC of relevant abstracts submitted for AGU and Cryosat users Workshop. Prepare and submit abstracts for other relevant meetings: Living Planet, EGU, ESA workshops, OSTS, Coastal Altimetry, and in 2014 COSPAR and the Liege Colloquium | ALL | A2_32 | 2012-11-30 | ongoing | Completed for AGU, Cryosat Users Worlkshop, EGU and ESA LP. any more abstracts for COSPAR, Liege colloquium
Complete and share Cryosat insturment parameter table as requested by SD | CNES, Altimetrics | A2_34 | 2013-01-12 | completed | Provided by CNES

## Closed AIs
description/description | Actionee | action / action | due date / date butoir | Status | Comment
Publish Project Management Plan on ftp site | SatOC | AI_01_01 | 2012-06-15 | Done
Provide SatOC with more detailed descriptions of Work Packages. | WP Leaders | AI_01_02 | 2012-06-22 | Done | NOC has provided details for WP3000TU Delft has provided details for WP2000 CLS has provided details for WP5000 isardSAT has provided details for WP4000
Generate and publish Risk Register on ftp site | SatOC | AI_01_03 | 2012-06-15 | Done
Coordinate with CNES and update WP descriptions (as included in the project plan) to include CNES contributions | WP Leaders | AI_01_06 | 2012-06-22 | Done
Circulate draft sub-contracts to all partners for review | SatOC | AI_01_07 | 2012-06-15 | Done
Review and IPR declaration as included in the draft contracts, DC to forward to ESA | ALL | AI_01_08 | 2012-06-22 | Done
Produce revised WP1000 description to incorporate extended schedule | Starlab | AI_01_09 | 2012-06-22 | Done
Liaise in submission / preparation of a poster for CoastALT | Starlab/SatOC | AI_01_10 | 2012-09-07 | Done | STARLAB prepared poster 11/09/12
Liaise with Pascal Bonnefond/OSTST organisers re possible CP4O presentation | ESA (JB) | AI_01_11 | 2012-06-29 | Done | Abstract provided to JB. Direct communications with Pascal Bonnefond established that an "official" poster would not be possible.
inform TP that CP4O will be reviewing CNES CPP product as well as ESA products | ESA (JB/SD) | AI_01_12 | 2012-06-22 | Done | TP agrees to use of CNES CPP data within scope of CP4O, but not to be distributed to 3rd parties
Provide consolidated and justified request for FBR data to ESA | SatOC/ isardSAT | AI_01_14 | 2012-06-29 | Done | Included in extended EOPI proposal. ESA is now maintaining an archive
Source all available detail on L1B processing chain | ESA (SD) | AI_01_17 | 2012-12-01 | Done | SD intends to issue a short Technical Note to outline the major steps of the L1b Processing Chain This will give to all the team a better overview of the SAR internal mechanisms This TN has been delivered to Robert Cullen for validation and then will be disclosed to all the CP4O team -see email of 31/08/12 TN has been checked by Marco Fornari and distributed by SD - 18/12/12
Provide more detail on known baseline IPF anomalies | ESA (SD) | AI_01_18 | 2012-06-22 | Done | Done 16/07/12
CLS/CNES to provide examples of SAR L1b CPP products | CLS, CNES | AI_01_20 | 2012-07-20 | Done | See email exchange of 13 July: CLS agreed to provide samples of SAR L1b cpp of may 2012 in a binary format and code to read them. F Boy approves (email 16/07/12). Later CNES provided a L1b product to ESA
To provide detail of WP4000 sub tasks and identify which team members will lead/contribute to which tasks | NOC | AI_01_21 | 2012-06-29 | Done
Noveltis / CNES to confirm that COMAPI validation report was presentation at 4th Coastalt workshop. | CNES / Noveltis | AI_01_26 | 2012-06-22 | Done | URL for presentation: http://www.coastalt.eu/files/portoworkshop10/pres/102_presentation_NOVELTIS_COMAPI.pdf Presentation also given at OSTST 2010 N Picot to provide validation reports
Specify changes to mode mask to provide SAR area to support sea floor altimetry applications. Location and duration needed. | DTU Space | AI_01_29 | 2012-06-22 | Done
Find detail on P Cipollini’s coastal index and circulate | SatOC | AI_01_31 | 2012-06-22 | Done | See email of 25/06/12, also available on ftp site
To find and distribute Walter Smith AGU presentation on retrieving mispointing from CryoSat. | ESA (PF) | AI_01_33 | 2012-06-22 | Done
Identify definite date for PR1 | SatOC | AI_01_40 | 2012-07-31 | Done | will be held at ESRIN, 22,23 November 2012
Update EOPI project to include CP4O, and requirement for FBR and L2 Interim products | SatOC | AI_01_41 | 2012-07-10 | Done
To provide access details to Kiruna calval server | ESA (TP) | AI_01_42 | 2012-07-16 | Done
Support Starlab to produce user questionnaires for Coastal Ocean (NOC), Polar Ocean (DTU Space) and Sea Floor Topography (DTU Space sub-themes. | NOC, DTU, CLS | AI_01_43 | 2012-07-26 | Done
Update PMP according to SD email of 30 July | SatOC | AI_01_44 | 2012-08-18 | Done
Review D1.1 (Requirements Baseline) and provide comments to STARLAB | All | A2_1 | 2012-12-07 | completed | D1.1 submitted to ESA for Review
Need to agree a statement from the whole CP4O team that can be relayed to the Cryosat Mission management regarding the quality of ESA Cryosat products and the consequent problems in using these products in the Cryosat Plus project. | TU Delft/ SatOC | A2_2 | 2012-12-07 | completed | DC has generated draft and SD, JB have updated. Sent to C2 mission manager on 30/01/2013
To provide information on the source of the L1b geo-corrections (i.e. where they come from each geo-correction) and if the L2-geocorrection are the same of L1b geo-corrections. | SD | A2_10 | 2012-12-14 | competed | see email from SD on 07/01/2013
TO updated Project Management Plan to take into account timetable changes (to WP2000 and WP4000) as accepted by ESA | DC | A2_11 | 2012-12-07 | competed
Produce agreed statement on decision to use CPP data in CP4O | ESA/SatOC/ All | A2_16 | 2012-12-14 | completed | same action as A2_2
To discuss U Porto need for RADS data to calculate WTC,and confirm availability | JF, RS | A2_21 | 2012-12-14 | competed | see email of 08/01/13
Liaise on timing and venue requirements for next meeting | ESA/SatOC | A2_33 | Spring 2013 | completed | 25-26 June, NOC

## ALL AIs
description/description | Actionee | action / action | due date / date butoir | Status | Comment
Publish Project Management Plan on ftp site | SatOC | AI_01_01 | 2012-06-15 | Done
Provide SatOC with more detailed descriptions of Work Packages. | WP Leaders | AI_01_02 | 2012-06-22 | Done | NOC has provided details for WP3000TU Delft has provided details for WP2000 CLS has provided details for WP5000 isardSAT has provided details for WP4000
Generate and publish Risk Register on ftp site | SatOC | AI_01_03 | 2012-06-15 | Done
Review and update Risk Register | ALL | AI_01_04 | 2012-06-22 | ongoing
Review timetable (in Project Management Plan) and advise SatOC of any potential delays or conflicts | ALL | AI_01_05 | 2012-06-22 | ongoing | Inputs received from CLS
Coordinate with CNES and update WP descriptions (as included in the project plan) to include CNES contributions | WP Leaders | AI_01_06 | 2012-06-22 | Done
Circulate draft sub-contracts to all partners for review | SatOC | AI_01_07 | 2012-06-15 | Done
Review and IPR declaration as included in the draft contracts, DC to forward to ESA | ALL | AI_01_08 | 2012-06-22 | Done
Produce revised WP1000 description to incorporate extended schedule | Starlab | AI_01_09 | 2012-06-22 | Done
Liaise in submission / preparation of a poster for CoastALT | Starlab/SatOC | AI_01_10 | 2012-09-07 | Done | STARLAB prepared poster 11/09/12
Liaise with Pascal Bonnefond/OSTST organisers re possible CP4O presentation | ESA (JB) | AI_01_11 | 2012-06-29 | Done | Abstract provided to JB. Direct communications with Pascal Bonnefond established that an "official" poster would not be possible.
Inform TP that CP4O will be reviewing CNES CPP product as well as ESA products | ESA (JB/SD) | AI_01_12 | 2012-06-22 | Done | TP agrees to use of CNES CPP data within scope of CP4O, but not to be distributed to 3rd parties
Identify, and source, relevant documents as WP2000 inputs | TU Delft, isardSAT, Noveltis, DTU | AI_01_13 | 2012-08-31 | Done | As reported at Progress Meeting
Provide consolidated and justified request for FBR data to ESA | SatOC/ isardSAT | AI_01_14 | 2012-06-29 | Done | Included in extended EOPI proposal. ESA is now maintaining an archive
Review plans for WP4000, WP5000 and consider how to validate / assess performance of all key processing steps | NOC, CLS | AI_01_15 | 2012-08-31 | ongoing | Should be included in DVP contributions
WP1000 and WP2000 to review available ESA information on CryoSat processing / products and identify gaps. | Starlab, TU Delft | AI_01_16 | 2012-12-13 |  | WP1000 completed, to be reported at Progress Meeting for WP2000 - still required? MN to confirm revised due date
Source all available detail on L1B processing chain | ESA (SD) | AI_01_17 | 2012-12-01 | Completed | SD intends to issue a short Technical Note to outline the major steps of the L1b Processing Chain This will give to all the team a better overview of the SAR internal mechanisms This TN has been delivered to Robert Cullen for validation and then will be disclosed to all the CP4O team -see email of 31/08/12 TN has been checked by Marco Fornari and distributed by SD - 18/12/12
Provide more detail on known baseline IPF anomalies | ESA (SD) | AI_01_18 | 2012-06-22 |  | Done 16/07/12
Identify and put in order anomalies in baseline IPF | ALL | AI_01_19 | 2012-06-29 | time expired | Will work from Level 1b
CLS/CNES to provide examples of SAR L1b CPP products | CLS, CNES | AI_01_20 | 2012-07-20 | Done | See email exchange of 13 July: CLS agreed to provide samples of SAR L1b cpp of may 2012 in a binary format and code to read them. F Boy approves (email 16/07/12). Later CNES provided a L1b product to ESA
To provide detail of WP4000 sub tasks and identify which team members will lead/contribute to which tasks | NOC | AI_01_21 | 2012-06-29 | Done | Done 05/11/12
WP2000 analysis to include identification of corrections needed on ESA FBR data | TU Delft | AI_01_22 | 2013-02-01 |  | Should be included in DVP contributions
To liaise and revise approach for RDSAR and SAR over open ocean, to cover generation and validation of products, and to take into account fact that CLS, CNES scheme starts from telemetered not FBR data. | Starlab / CLS | AI_01_23 | 2012-09-28 | Done | CLS propose changing the due date to end September, Agreed as this doesn’t impact the proposed timetable for milestons
Develop possible assessment approach using simulated products. | CNES and CLS | AI_01_24 | 2012-11-30 |  | Action ongoing : "the S3 SPS has been installed on the CNES Linux Cluster. We have generated one simulation lasting 90 seconds in SAR mode over ocean. It tooks about 125 CPU hours … We need to carefully validate this SPS installation and to contact Salvatore to define the simulation context."
Provide from RADs along track parameters needed for WTC computation and validation | TU Delft | AI_01_25 | Spring 2013
Noveltis / CNES to confirm that COMAPI validation report was presentation at 4th Coastalt workshop. | CNES / Noveltis | AI_01_26 | 2012-06-22 | Done | URL for presentation: http://www.coastalt.eu/files/portoworkshop10/pres/102_presentation_NOVELTIS_COMAPI.pdf Presentation also given at OSTST 2010 N Picot to provide validation reports
Specify number of passes needed and to identify alternative region for investigation of SARIN data on tracks perpendicular to coast | isardSAT | AI_01_27 | 2012-07-29 | Done | About 20, Final requirements to be confirmed. Other possible areas include Iceland.
Provide more detailed WP description to describe planned processing steps in SARIN coastal work | isardSAT | AI_01_28 | 2012-07-13 | Done | See PM1 presentation
Specify changes to mode mask to provide SAR area to support sea floor altimetry applications. Location and duration needed. | DTU Space | AI_01_29 | 2012-06-22 | Done
Send PF a short note about low volume (< 25%) of LRM data retrieved in area to N of Britain. | DTU Space | AI_01_30 | 2012-12-03 |  | PF confirmed would still like to receive
Find detail on P Cipollini’s coastal index and circulate | SatOC | AI_01_31 | 2012-06-22 | Done | The same presentation was also given at the OSTST meeting in 2010.
Include recommendations on metrics for impact assessment in outputs of WP2000 | TU Delft | AI_01_32 | 2013-02-01 |  | MN to confirm due date
To find and distribute Walter Smith AGU presentation on retrieving mispointing from CryoSat. | ESA (PF) | AI_01_33 | 2012-06-22 | Done
Issue a draft of WP5000 assessment metrics for comment | CLS (SL) | AI_01_34 | 2012-10-19 | Done | See PM1 presentation: PM1_WP5000_Moreau.pptx
Summarise approach for sea floor and polar oceans and copy to DTU space for comment | CLS (SL) | AI_01_35 | 2012-10-19 | Done | See PM1 presentation: PM1_WP5000_Moreau.pptx
To coordinate plans for WP4000 and WP5000 | CLS (SL) and NOC (CG) | AI_01_36 | 2013-03-30 | ongoing | email discussions
Provide SatOC with list of Expert Group members | ESA (JB) | AI_01_37 | 2013-02-22 | completed | JB has invited experts to coordiated CP4O mid-term review / SAR Altimetry Workshop
Review the outline proposals for additional work in Technical Proposal and ask more detail for those of interest | ESA | AI_01_38 | May 2013? | ongoing | Maintain and update list as annex to Project Plan
Consider possibility of closer coordination of activities between Land and ocean themes at coast and potential for linking of products | ALL | AI_01_39 | 2012-07-20 | time expired | Closed but continue to bear in mind as "business as usual", but land project likely to be delayed
Identify definite date for PR1 | SatOC | AI_01_40 | 2012-07-31 | Done | will be held at ESRIN, 22,23 November 2012
Update EOPI project to include CP4O, and requirement for FBR and L2 Interim products | SatOC | AI_01_41 | 2012-07-10 | Done
To provide access details to Kiruna calval server | ESA (TP) | AI_01_42 | 2012-07-16 | Done
Support Starlab to produce user questionnaires for Coastal Ocean (NOC), Polar Ocean (DTU Space) and Sea Floor Topography (DTU Space sub-themes. | NOC, DTU, CLS | AI_01_43 | 2012-07-26 | Done
Update PMP according to SD email of 30 July | SatOC | AI_01_44 | 2012-08-18 | Done
NOC to respond to SD's email 12 July regarding SoA review on SAR data over ocean. To change SAR analysis to FBR. Confirm if this is WP2100 (product) or WP2200 (Model) | NOC | AI_01_45 | 2012-10-26 | Done | Accepted - but with some restriction
Review D1.1 (Requirements Baseline) and provide comments to STARLAB | All | A2_1 | 2012-12-07 | completed | D1.1 submitted to ESA for Review
Need to agree a statement from the whole CP4O team that can be relayed to the Cryosat Mission management regarding the quality of ESA Cryosat products and the consequent problems in using these products in the Cryosat Plus project. | TU Delft/ SatOC | A2_2 | 2012-12-07 | completed | DC has generated draft and SD, JB have updated. Sent to C2 mission manager on 30/01/2013
CLS to review effort needed to lead WP2200 and 2400 and decide if they can do this | CLS | A2_3 | 2012-12-07 | time expired? | Draft of PAR in preparation, 7th May
Include comment on Sandwell retracker in WP2000 review | NOC | A2_4 | 2012-12-07 | completed | included in CP4O_WP2200_NOC_input.docx
To be confirmed: To provide algorithm on generation of sigma-0? | MF | A2_5 | 2012-12-07
Advise NOC/SatOC of relevant initiatives that should be included in WP2000 review (LRM and SAR data over coastal and open ocean) | All | A2_6 | 2012-12-07 | time expired? | Draft of PAR in preparation, 7th May
Review Crysoat-2 document list when provided by Starlab | ALL | A2_7 | TBD
Check if RDSAR needs modification to work on real C-2 data. | Starlab | A2_8 | 2012-12-07 | ongoing | Waiting for the AI_01_22 ( WP2000 analysis to include identification of corrections needed on ESA FBR data) to be completed and also waiting for the FBR to arrive. Due date to be revised
To provide an Executive Summary of WP2000, including key findings / conclusions, before Christmas | TU Delft | A2_9 | 2012-12-21 | time expired? | Draft of PAR in preparation, 7th May
To provide information on the source of the L1b geo-corrections (i.e. where they come from each geo-correction) and if the L2-geocorrection are the same of L1b geo-corrections. | SD | A2_10 | 2012-12-14 | competed | see email from SD on 07/01/2013
TO updated Project Management Plan to take into account timetable changes (to WP2000 and WP4000) as accepted by ESA | DC | A2_11 | 2012-12-07 | competed
Produce document on σ0 calculation implemented in RADS | RS | A2_12 | 2012-12-07
Source documentation on σ0 calculation implemented in IPF | ESA (SD, MF)? | A2_13 | 2012-12-07
CNES to respond to requests to modify CPP product as described in 4.33 | CNES | A2_14 | TBD - ongoing | completed? | available through link at https://earth.esa.int/web/guest/missions/cryosat/ipf-baseline
Produce agreed statement on decision to use CPP data in CP4O (links to A2_2) | ESA/SatOC/ All | A2_15 | TBD
To updated data requirements spreadsheet | All | A2_16 | 2012-12-14 | completed | same action as A2_2
Advise isardSAT / CNES (cc SatOC) on requirements for CPP SAR data in WP4000. Specify location (polygon) and time period. | All | A2_17 | 2012-12-14 | completed?
Advise when (and if!) requested CPP data for WP4000 can be made available | FB | A2_18 | 2012-11-30 | completed? | NOC and Starlab have provided requirements
Identify best approach to allow for mispointing in CPP products retrieved for WP4000 | FB, RS | A2_19 | 2012-12-14 | completed | CPP data produced and available. See FP email 4th April
To discuss U Porto need for RADS data to calculate WTC,a nd confirm availability | JF, RS | A2_20 | TBD | ongoing?
Provide (historic) CS-2 orbit files with time, lat, long (and if possible surface type) | ESA (SD, MF) | A2_21 | 2012-12-14 | competed | see email of 08/01/13
Request that information be provided on which star trackers is used be made available (important for SARIN applications) | ESA (SD?) | A2_22 | TBD |  | underway
CNES to make mispointing file available to CP4O, and communicate the estimates values of new biases in Roll and Pitch. | CNES | A2_23 | 2013-01-27
CNES and NOOA to iterate mispointing analyses and report back to CP4O team on recommendations for processing / retracking. | CNES, RS | A2_24 | 2012-12-07
Provide specifications of test data set coverage and approaches for product processing and validation for RDSAR and SAR Open Ocean themes in WP4000 | Starlab, CLS | A2_25 | 14/12/12? | completed? | See emails between Rs and NP ending 01/03/13
Provide feedback to CLS on proposed assessment metrics for WP5000 | All | A2_26 | TBD
Provide feedback to CLS on proposed approach to polar oceanography and sea floor altimetry in WP5000 | DTU | A2_27 | 2012-12-14 | partially completed | Coverage provided, Starlab to provide input to DVP.
Liaise with CB to find information on internal path delay (for LRM and SAR) | SatOC | A2_28 | TBD (06/13?) |  | to be clarified
Advise SatOC of relevant abstracts submitted for AGU and Cryosat users Workshop. Prepare and submit abstracts for other relevant meetings: Living Planet, EGU, ESA workshops, OSTS, Coastal Altimetry, and in 2014 COSPAR and the Liege Colloquium | ALL | A2_29 | 2012-12-14 | ongoing
Liaise on timing and venue requirements for next meeting | ESA/SatOC | A2_30 | 2012-12-14 | ongoing
Liaise with CB to find information on internal path delay (for LRM and SAR) | SatOC | A2_31 | 2012-12-07
Advise SatOC of relevant abstracts submitted for AGU and Cryosat users Workshop. Prepare and submit abstracts for other relevant meetings: Living Planet, EGU, ESA workshops, OSTS, Coastal Altimetry, and in 2014 COSPAR and the Liege Colloquium | ALL | A2_32 | 2012-11-30 | ongoing | Completed for AGU, Cryosat Users Worlkshop, EGU and ESA LP. any more abstracts for COSPAR, Liege colloquium
Liaise on timing and venue requirements for next meeting | ESA/SatOC | A2_33 | Spring 2013 | completed | 25-26 June, NOC
Complete and share Cryosat insturment parameter table as requested by SD | CNES, Altimetrics | A2_34 | 2013-01-12